## Tabelle1
NEW OPTIMIZER SYNCROTESS (FIFO)
No. | Requesting Country | Description | Detail | Cherwell | HC Jira | ST Jira | In scope | Status | Expected update | Questions back to requester | Comments
1 | BENE CCR | Optimized breakhandling (break handling part 2) | Optimized breakhandling (break handling part 2) | 806889 |  |  | yes | await INFORM proposal | End Nov 22 |  | Excel file prepared 2020 - INFROM aware? Parameters per country (Break variant 1 / 2 + legal break time requirements + Optimization RT+PP)
2 | BENE POL | Planning of announced Collect orders | details in Collect order meeting minutes from 24.03.2022 by EMG. | 807241 |  |  | ? | await INFORM proposal | End Nov 22 |  | Step 1 of solution already in progress with INFORM for current optimizer. Step 2 will be possible with change of loading capacity to m³/hr in MIXOR.
3 | BENE CCR | Multi Shifts planning | 3 shifts to be possible to plan for. Regret already has that function - copy? | 170175 |  |  | yes | to be discussed with INFORM | End Nov 22 |  | 2022-10-24: Feedback on Multi shift abstract from INFORM has been discussed on 24.10.22 with Ronald/CE/CCR. Still gaps.
4 | CCR | Possibility to fix loads to trucks without wrong on-time color indication | Details in HCE-3025: https://gs2-jira.inform-software.com/browse/HCE-3025 Remark 01.12.: Current issue with handling fixed proposals with FIFO, will be considered in MIXOR |  |  | HCE-3025 | ? | to be discussed with INFORM | End Nov 22
5 | POL | Handling of sales orders passing midnight | Business is requesting a solution in the new optimiser (FIFO variant) for handling PP and RT of sales orders that pass midnight (proposals should be stated as well after midnight) Remark 01.12.: FIFO planning midnight to midnight - will be enhanced with MIXOR | 1234437 |  |  | ? | clarify request | End Nov 22
6 | POL | Multi Shifts triggered by ZRM (interface discussion) | Business is requesting a solution to maintain up to 3 drivers for one truck in ZRMx transaction. In addition, that data needs to be transmitted to SyncroTESS. Shift/Roster planing triggerd by ZRM + maintained drivers Currently drivers are informed via RPA (Robotics Process Automation) and SMS That roster is maintained manually in an Excel file RPA maybe using ZSD_ROSTER (check requirements) | 1234459/1234469 |  |  | ? | clarify request | End Nov 22 |  | Optimization for 2 shifts (for sure) 3 TBC
7 | BENE POL | Redirecting trucks in PrePlanning to other plants | Business is requesting a possibility to assign in PrePlanning a different plant/location to a truck after 1,2,3 jobs or at a specific time. As example: Truck starts first shift at plant PL3H, after first job, the truck needs to relocate to plant PL3V and continue jobs there. At the end of the first shift it parks at plant PL3V or it can finish at the original plant PL3H. It should be possible to setup that example in PrePlanning and apply it to RT as well. | 1234473 |  |  | ? | clarify request | End Nov 22 |  | - is it same as request nr 10 (BENE)? (The proposals during the pre-planning is the same) - is workaround to use several shifts an alternative? - Pre-plan or real-time optimization should determine the actual assigment? - Should truck movements being proposed in pre-planning? Or manual entry only?
8 | POL CCR | Optim ON trucks after applying preplan to get proposals as well | Polish business is requesting a solution to a problem with trucks getting no proposals (before they sign in) if they were not in the preplan. Scenario: Preplan is created and applied for tomorrow. On the day of execution, we get an additional sales order and have to get an additional truck to handle the workload. Once this new truck is set to optim/pp on, it doesnt get any proposals in both RT and OEV. Only after this truck signs in, it starts to get proposals. | 1234490 |  |  | ? | clarify request | End Nov 22
9 | BENE CCR DE | Variable Loading time | Loading time min/m³ per material (Idea: Minutes per batch per material) "Overall concept": Time before loading + time/m³ + Time after loading Question: Wet/dry batching? Discuss: Has effect on 9 "Loading capacity" min/m³ maintained in LAB-System, transferred to Material Master SAP, to ST via Order HM further internal discussions required
10 | BENE CCR DE | Loading capacity: Qty per hour | Loading capacity in m³/hr instead of loads/hr Based on material |  |  |  | ? | in progress by Inform | End Nov 22 |  | Conecept in progress by Inform
11 | AUS | Loading Capacity: Plant Capacity split between DGs | One plant in 2 DGs - Loading capacity should be shared between those two DGs Approach: Optimizer should decide on order book on how to divide the loading capacity between the DGs Challenges MIXOR: Optimization runs are individual and independant per DG
12 | BENE | Loading Capacity Factors | Reduction of loading capacity in % (reduction of delivered orders) Function exists but is not taken into consideration for loading capacity |  | PBSCM-13
13 | BENE | Truck movement | Insufficient truck movement (Transfer vs Regret) between plants in pre-plan. Topic for New Optimizer + not only pre-planning but as well real time Expected that Optimizer already in pre-plan moves trucks to plants where they are needed. "Behaviour like it was in Regret" "Move around but not too much" |  |  |  | ? | clarify request | End Nov 22 | How much truck movement would be correct? | - is it same as request nr 7 (POL)? - is workaround to use several shifts an alternative?
14 | BENE | Sign-on latency stronger | insufficient latency make the parameter to prevent the optimizer from changing the proposals based on not signed on trucks The current functionality is not to work in FIFO |  |  |  | ? | clarify request | End Nov 22 |  | Competence Team?
15 | BENE | Automatic assignment | AUS only currently Currently switch on truck level Additional idea: On order level