## Tabelle1
NEW OPTIMIZER SYNCROTESS (FIFO)
No. | Requesting Country | Description | Detail | Cherwell | HC Jira | ST Jira | In scope | Status | Expected update | Questions back to requester | Comments
1 | BENE CCR | Optimized breakhandling (break handling part 2) | Optimized breakhandling (break handling part 2) | 806889 |  |  | yes | await INFORM proposal | End Nov 22 |  | Excel file prepared 2020 - INFROM aware? Parameters per country (Break variant 1 / 2 + legal break time requirements + Optimization RT+PP)
2 | BENE POL | Planning of announced Collect orders | details in Collect order meeting minutes from 24.03.2022 by EMG. | 807241 |  |  | ? | await INFORM proposal | End Nov 22 |  | Step 1 of solution already in progress with INFORM for current optimizer. Step 2 will be possible with change of loading capacity to m³/hr in MIXOR.
3 | BENE CCR | Multi Shifts planning | 3 shifts to be possible to plan for. Regret already has that function - copy? | 170175 |  |  | yes | to be discussed with INFORM | End Nov 22 |  | 2022-10-24: Feedback on Multi shift abstract from INFORM has been discussed on 24.10.22 with Ronald/CE/CCR. Still gaps.
4 | CCR | Possibility to fix loads to trucks without wrong on-time color indication | Details in HCE-3025: https://gs2-jira.inform-software.com/browse/HCE-3025 Remark 01.12.: Current issue with handling fixed proposals with FIFO, will be considered in MIXOR |  |  | HCE-3025 | ? | to be discussed with INFORM | End Nov 22
5 | POL | Handling of sales orders passing midnight | Business is requesting a solution in the new optimiser (FIFO variant) for handling PP and RT of sales orders that pass midnight (proposals should be stated as well after midnight) Remark 01.12.: FIFO planning midnight to midnight - will be enhanced with MIXOR | 1234437 |  |  | ? | clarify request | End Nov 22
6 | POL | Multi Shifts triggered by ZRM (interface discussion) | Business is requesting a solution to maintain up to 3 drivers for one truck in ZRMx transaction. In addition, that data needs to be transmitted to SyncroTESS. Shift/Roster planing triggerd by ZRM + maintained drivers Currently drivers are informed via RPA (Robotics Process Automation) and SMS That roster is maintained manually in an Excel file RPA maybe using ZSD_ROSTER (check requirements) | 1234459/1234469 |  |  | ? | clarify request | End Nov 22 |  | Optimization for 2 shifts (for sure) 3 TBC
7 | BENE POL | Redirecting trucks in PrePlanning to other plants | Business is requesting a possibility to assign in PrePlanning a different plant/location to a truck after 1,2,3 jobs or at a specific time. Workshop example: Blocking + location (send-to) in pre-planning and taken over into RT How restrictive should be proposals? (Proposal would finish 10:05, blocker would be 10:00) Time interval around it? BeNe example: x POL example: Truck starts first shift at plant PL3H, after first job, the truck needs to relocate to plant PL3V and continue jobs there. At the end of the first shift it parks at plant PL3V or it can finish at the original plant PL3H. It should be possible to setup that example in PrePlanning and apply it to RT as well. | 1234473 |  |  | ? | clarify request | End Nov 22 |  | - is it same as request nr 10 (BENE)? (The proposals during the pre-planning is the same) - is workaround to use several shifts an alternative? - Pre-plan or real-time optimization should determine the actual assigment? - Should truck movements being proposed in pre-planning? Or manual entry only?
8 | POL CCR | Optim ON trucks after applying preplan to get proposals as well | Polish business is requesting a solution to a problem with trucks getting no proposals (before they sign in) if they were not in the preplan. Scenario: Preplan is created and applied for tomorrow. On the day of execution, we get an additional sales order and have to get an additional truck to handle the workload. Once this new truck is set to optim/pp on, it doesnt get any proposals in both RT and OEV. Only after this truck signs in, it starts to get proposals. 15.12.22: Will be in MIXOR Not only additional truck but as well replacing a rostered/SAS truck Idea: Enter SAS time for not rostered truck | 1234490 |  |  | ? | clarify request | End Nov 22
9 | BENE CCR DEU | Variable Loading time | Loading time min/m³ per material (Idea: Minutes per batch per material) "Overall concept": Time before loading + time/m³ + Time after loading Question: Wet/dry batching? Discuss: Has effect on 9 "Loading capacity" min/m³ maintained in LAB-System, transferred to Material Master SAP, to ST via Order HM further internal discussions required
10 | BENE CCR DE | Loading capacity: Qty per hour | Loading capacity in m³/hr instead of loads/hr Based on material |  |  |  | ? | in progress by Inform | End Nov 22 |  | Conecept in progress by Inform
11 | AUS | Loading Capacity: Plant Capacity split between DGs | One plant in 2 DGs - Loading capacity should be shared between those two DGs Approach: Optimizer should decide on order book on how to divide the loading capacity between the DGs Challenges MIXOR: Optimization runs are individual and independant per DG
12 | BENE | Loading Capacity Factors | Reduction of loading capacity in % (reduction of delivered orders) Function exists but is not taken into consideration for loading capacity Example: Due to collects in the morning (usecase of REGRET) 15.12.22: Additional use cases ("partial plant break downs")? Should be rather enhanced "planned plant breakdowns"? Due to SAP authorizations, maintenance should be in ST? Business case: 2 legs, one gone during the day |  | PBSCM-13
13 | BENE | Truck movement | Insufficient truck movement (Transfer vs Regret) between plants in pre-plan. Topic for New Optimizer + not only pre-planning but as well real time Expected that Optimizer already in pre-plan moves trucks to plants where they are needed. "Behaviour like it was in Regret" "Move around but not too much" Linked to 7 |  |  |  | ? | clarify request | End Nov 22 | How much truck movement would be correct? | - is it same as request nr 7 (POL)? - is workaround to use several shifts an alternative?
14 | BENE | Sign-on latency stronger | insufficient latency make the parameter to prevent the optimizer from changing the proposals based on not signed on trucks The current functionality is not to work in FIFO |  |  |  | ? | clarify request | End Nov 22 |  | Competence Team?
15 | BENE | Automatic assignment | AUS only currently Currently switch on truck level Additional idea: On order level
16 | DEU | Truck movement | Transformations switched on in pre-plan but not in real-time Pre-Plan should include truck movements Real time not Remark 12.01: High risk, planning and real-time is different Idea: Maybe different parameters for PP or RT Remark meeting Germany 19.01.: Pre-planning should do truck movements, in real-time those movements should be taken as fixed Idea: Create PP scenario, observe movements, delete scenario, make movements manually Next steps: Inform to check for efforts for FIFO and MIXOR (pre-plan transformation on/real-time transformation off) as well checking for options which are currently available for supporting/highlighting awareness of truck movements in RT
17 | DEU | Plus Load/unconfirmed orders (?) | Consider plus load in real time (like in OEV) Remark 12.01.: Plus load is seen in RT, BeNe will provide an example snap shot "Write after confirm plus load it is visible for a couple of minutes, then it is gone" Optimizer issue or only highlight? Remark meeting Germany 19.01.: Hightlight: Yes 1. Planned like usual delivery, but optical different 2. Pop-up or simaliar Optimizer: Close to end of shift, truck is sent home, should not happen if a possible plus load is left Truck capacity should be kept available
18 | DEU | FAS/SAS rounded | Round down to 5 minute steps (08:53 -> 08:50) Remark 12.01.: “We are already early, we would be even earlier” Remark meeting Germany 19.01.: Low priority Idea: Before sending pre-plan, hit button and round
19 | DEU | Pump order priority | Delivery flow for pump orders should be prioritized Remark 12.01.: Option: Adjust other orders (postpone or change delivery flow), very day-to-day/situation dependend decisions for prioritization Idea: On-going vs new starting orders prioritization (there has already been a SCR on this which got eliminated in the maintenance process. SCR number to be provided here)
20 | DEU | Real time traffic | Real time traffic information taken as travel time
21 | DEU | Production costs | Consider production costs
22 | ? | Loading time depending on qty and material
23